Hi Ashish,
Just to clarify my intent in the simplest possible way:

• The current BackOffice at https://backoffice.idbforge.be/nl is the Baseline (as of [DATE]).
• Except for the items explicitly listed in Scope 1 / Annexure 1 (AC codes), the rest was not commented on because it is working.
• Therefore, Scope 1 is strictly limited to fixing what is listed in Annexure 1 — nothing more.

My only additional requirement is non-regression:
If code changes are made to fix Scope 1 items, it is not acceptable that parts which were working in the Baseline suddenly stop working. Any such regression should be treated as a defect and corrected at no extra cost.

So in short: Baseline (as-is) + Scope 1 fixes, without regressions.

Point 1 — Supersession (prior agreements / references) – replaced by Baseline & Non-Regression (Scope 1):
The Parties acknowledge that the current BackOffice available at https://backoffice.idbforge.be/nl (the “Baseline”) is operational except for the specific items documented in Scope 1 / Annexure 1. The Services under Scope 1 are limited strictly to the changes required to resolve the Scope 1 items.
The Service Provider shall implement the Scope 1 changes in a manner that does not introduce regressions. For the avoidance of doubt, functionality that is working in the Baseline shall continue to work after the Scope 1 delivery and during the warranty period, except where a change is explicitly required by an AC code in Annexure 1.
Any regression introduced by the Service Provider shall be treated as a defect and corrected at no additional cost.

Point 4 & 9 — Acceptance / Closure (no silence, with reminder):
If the Client does not respond within 10 Client Working Days (Europe/Brussels), the Provider will send a written reminder. If there is still no response within 5 additional Client Working Days after the reminder, the item is deemed accepted/closed, provided no documented blocking issues were raised by the Client within the initial UAT window.

Point 5 — Penalties (deduction & sole remedy for delays):
Delay Penalty (delivery scenario): 1% per week of delay, capped at 10%, deductible from the final payment (sole monetary remedy for delay).
Non-Completion / Termination for Cause: if the Agreement is terminated for cause due to non-delivery / abandonment or two consecutive rejections for failure to meet Annexure 1 (AC codes), the penalty cap increases to 20% (as a non-completion fee), and becomes immediately deductible/set-off against any outstanding amounts or refundable if no amounts remain due.
10% cap for delays when the project completes.
20% cap only if termination for cause due to non-completion/non-delivery.

Point 7 — Third-party developers during active Scope 1:
During Scope 1, third-party work requires Provider’s written approval (not unreasonably withheld).
Exception: for Critical Issues (outage/data integrity/security) not mitigated within the critical issue handling timeline defined in Point 8 (acknowledge within 1 Client Working Day; mitigation within 2 Client Working Days or a written action plan), Client may perform emergency remediation with full documentation shared immediately.

Point 10 — Governing law / venue:
I agree arbitration is virtual and enforcement follows assets.
However, governing law still matters for interpretation. Let’s use a neutral governing law (England & Wales) with virtual arbitration. Enforcement remains in the defendant’s jurisdiction if required.